## Maturity
Level | 1 | 2 | 3 | 4 | 5
1. Portfolio strategic governance | The organization attempts to align individual initiatives with organisational objectives, but there is an ad hoc, inconsistent, and ineffective oversight of initiatives. | The portfolio is recognized by the organisation, but there is still little overall leadership and direction for the process. Initiatives may be initiated and run without full regard to the organisational goals, priorities, and targets. | The principles of portfolio management are understood, practiced to a consistent standard, and underpin the governance framework. | The initiatives within the portfolios are prioritised in terms of their contribution to the organization’s strategic objectives and overall level of risk. | The portfolio of change is collectively sufficient to achieve the desired contribution to strategic objectives
2. Portfolio management | The organization recognizes the portfolio(s) but has little or nothing in terms of documented processes, tools, or standards for managing the portfolio(s). | There are some pockets of portfolio management discipline within individual departments, but this is based on key individuals rather than as part of a comprehensive and consistent organization-wide approach. | Portfolio management processes and tools are centrally defined, documented, and understood, as are roles and responsibilities for controlling the portfolio. | Portfolio management processes exist and are proven. Portfolio management has established metrics against which success can be measured including underpinning tools | Portfolio is managed consistently to ensure efficient and effective delivery. The portfolio mgmt. system is aligned to foster agility, quality, and speed
3. Financial management | Portfolio oversight of the financial aspects of initiatives may be recognized but there is little or no organizational investment control. | There are some pockets of good business case production and some, usually departmental, structures to oversee investment decisions. | There are established central standards for the investment management process as well as tracking cost control | The organization has robust financial control of its investment decisions and the approval and monitoring of initiatives. Uses measurement and analysis of performance to manage. | Funding outcomes and teams is enabled through the organisations financial management approach focusing on investment to achieve the strategic aims and objectives
4. Agile - Planning | Where product backlog refinement and prioritisation exist, they have been developed in isolation by individual teams | Product backlog refinement and prioritisation is recognised as a key component for teams with localised approaches in place | The team consistently refine and prioritise their product backlog using a centrally defined approach | Our value stream and team’s product refinement and prioritisation are integrated with organisational product decomposition and prioritisation approach including dependency mgmt. | Our value stream and team’s product refinement and prioritisation are embedded with organisational product decomposition and prioritisation approach to achieve the strategic objectives
5. Coaching and capability | No coaching or training program established centrally. Some localised and individual coaching occurring. | Coaching practice established centrally with associated funding. Coaching guidelines and tools are developed and utilised. | Identification of gaps, coaching requirements, coaching methods and change from coaching is systematic. | Coaching is aligned with competency models and the broader delivery approach. Coaching is focus on supporting key strategic business objectives. | The coaching practice makes a quantifiable return on investment – this is known. Coaching is common practice – leaders as coaches. The organisation is a learning organisation and change is common
6. Resource management | Portfolio resource requirements are recognized but not systematically managed. Resource allocation is ad hoc, with little profiling of resources to meet specific initiative requirements. | Team resource management occurs locally with no central alignment. | The organization has started to develop portfolio resource management processes and improve the identification and allocation of resources connected to team processes. | Team resource mgmt. (velocity, feature estimation) is integrated within the organisation resource mgmt. approach. | Team resource mgmt. (velocity, feature estimation) is embedded within the organisation resource mgmt. approach focusing on maximising the capacity and capability to achieve our strategic aims and objectives
7. Risk management | There may be a growing recognition that risks need to be managed and that they can threaten the successful delivery of the portfolio. | There is a top-down approach to risk identification, focusing on organizational initiatives. These approaches are inconsistent, not interrelated and often fail to address risk management. | Portfolio risks are identified and quantified, and mitigation plans are developed. Risk management across the portfolio is based on a common, centrally managed process. | The organization’s appetite for risk and the balance of risk and benefit across the portfolio are continually reviewed and managed. | Portfolio risk management is embedded within the organisations risk mgmt. approach
8. Stakeholder mgmt. | Stakeholder engagement and communication are rarely used by portfolios as elements of the delivery toolkit. | Some parts of the portfolio are communicating effectively, but this is linked more to the personal initiative of portfolio managers than to a structured approach deployed by the organization. | There is a centrally managed and consistent approach to stakeholder engagement and communications, used by all within the portfolio. | Sophisticated techniques are used to analyse and engage the stakeholder community, and quantitative information is used to underpin the assessment of effectiveness. | Communications are being optimized from extensive knowledge of the stakeholder environment, to enable the portfolio to achieve the strategic objectives
9. Change management | Change management is rarely used by value streams and teams as elements of the delivery toolkit. | Some parts of the portfolio are managing change effectively, but this is linked to the personal initiative of portfolio managers than to a structured approach deployed by the organization. | There is a centrally managed and consistent approach to change management used by all within the portfolio. | Sophisticated techniques are used to manage change, and quantitative information is used to underpin the assessment of effectiveness. | Change management is delivering clear change adoption to enable the portfolio to achieve the strategic objectives
10.Benefits management | Where benefits management approach exists, they have been developed in isolation by individual teams, value streams or departments | The development of the investment cycle is increasing the awareness and importance of identifying benefits and subsequently tracking their achievement. | There is a centrally managed framework used for defining and tracking the delivery and realization of portfolio-level benefits. | The benefits realization and management process are well established, measurable and is integrated into how the organization manages itself including performance mgmt. | Benefits realisation is maximised to provide the greatest return. Benefits are embedded within change and performance mgmt. approaches focusing on outcomes to achieve strategic aims.